## Plan
Template by Syntra — AI project management · syntra.tymko.tech
Project plan with a Gantt chart
Project |  | tymko.tech website relaunch
Project start |  | 2026-11-02
Change the start date and the tasks — the bars on the weeks redraw themselves.
# | Phase | Task | Owner | Start | End | Days | Done, % | Status
1 | Preparation | Collect requirements from departments | Olena K. |  |  |  | 100% | Done
2 | Preparation | Approve the site structure | Ivan P. |  |  |  | 100% | Done
3 | Design | Prototype the key pages | Marta D. |  |  |  | 60% | In progress
4 | Design | Get the design signed off | Ivan P. |  |  |  | 0% | Not started
5 | Build | Build the pages | Andrii S. |  |  |  | 0% | Not started
6 | Build | Move the content | Olena K. |  |  |  | 0% | Not started
7 | Launch | Test and fix | Andrii S. |  |  |  | 0% | Not started
8 | Launch | Go live and redirect old URLs | Andrii S. |  |  |  | 0% | Not started