## Register
Template by Syntra — AI project management · syntra.tymko.tech
Project risk register
Probability and impact go from 1 to 5. Score and level are calculated; the matrix is on its own sheet.
# | Risk | Category | Probability (1–5) | Impact (1–5) | Score | Level | Owner | Response | Due | Status
1 | Design sign-off is late | Schedule | 4 | 3 |  |  | Ivan P. | Fixed review slots twice a week | 2026-11-16 | Open
2 | Content not ready for launch | Scope | 3 | 4 |  |  | Olena K. | Page list with owners and deadlines | 2026-11-23 | Open
3 | Search rankings drop after the move | Technical | 2 | 5 |  |  | Andrii S. | 301 redirect map and Search Console checks | 2026-11-30 | Monitored
4 | Key developer on holiday | People | 2 | 3 |  |  | Ivan P. | Documentation and a second developer | 2026-12-07 | Open

## 5×5 matrix
Number of risks in the cell
Probability ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5
4
3
2
1