## Status report
Template by Syntra — AI project management · syntra.tymko.tech
Project status report
Project | tymko.tech website relaunch
Period | 2–15 Nov 2026
Project manager | Ivan P.
Overall status | Amber
Health by area
Scope | Green
Schedule | Amber
Budget | Green
Team | Green
Summary
Requirements and structure approved. Design is 3 days late on sign-off — we recover it during the build.
Done this period
Requirements from 4 departments; a 24-page structure; prototypes of the home and catalogue pages.
Next period
Sign off the design by 20 Nov; start the build; assign content owners.
Milestones
Milestone | Planned | Forecast | Status
Structure approved | 6 Nov | 6 Nov | Done
Design signed off | 20 Nov | 23 Nov | At risk
Go live | 28 Dec | 28 Dec | On track
Risks and issues
Risk / issue | Impact | Response | Owner
Design sign-off | Schedule +3 days | Fixed review slots | Ivan P.
Content | Launch may slip | Page list with deadlines | Olena K.
Decisions needed
Approve the budget for a team photo shoot (by 25 Nov).
Budget, €
Plan | Actual | Forecast | Variance
12000 | 3800 | 11500